## Merge Plan
SaaS Merge - Execution Plan
Window: Tue 8 Sep 2026 to Thu 1 Oct 2026 ¦ 18 working days ¦ Yellow cells with blue text are yours to edit
ID | Milestone | Task | Owner | Start | End | Work Days | Depends On | Status | % Done | Critical Path | Notes / Exit Criteria
0.1 | M0. Program Setup | Name single decision owner and escalation path | Exec Sponsor | 2026-09-08 | 2026-09-08 | 1 |  | Not Started | 0% | Y | One named person can break ties without a committee
0.2 | M0. Program Setup | Stand up shared tracker, comms channel and daily 15-min standup | PM | 2026-09-08 | 2026-09-08 | 1 | 0.1 | Not Started | 0% | Y | Both teams working from one board, not two
0.3 | M0. Program Setup | Agree what 'done by 1 Oct' means vs what slips to Q4 | Exec Sponsor / PM | 2026-09-08 | 2026-09-09 | 2 | 0.1 | Not Started | 0% | Y | Written scope statement signed by both product owners
0.4 | M0. Program Setup | Declare feature freeze and change-freeze windows | Eng Leads | 2026-09-09 | 2026-09-09 | 1 | 0.3 | Not Started | 0% | Y | No non-merge releases to either system during cutover week
0.5 | M0. Program Setup | Open RAID log (risks, assumptions, issues, dependencies) | PM | 2026-09-09 | 2026-09-09 | 1 | 0.2 | Not Started | 0% | N | Log live and reviewed at every standup
1.1 | M1. Discovery & Inventory | Inventory System A: services, repos, infra, runtimes, versions | Eng Lead A | 2026-09-08 | 2026-09-10 | 3 | 0.2 | Not Started | 0% | Y | Single source-of-truth inventory sheet
1.2 | M1. Discovery & Inventory | Inventory System B: services, repos, infra, runtimes, versions | Eng Lead B | 2026-09-08 | 2026-09-10 | 3 | 0.2 | Not Started | 0% | Y | Single source-of-truth inventory sheet
1.3 | M1. Discovery & Inventory | Export both data models / ERDs plus row counts per entity | Data Lead | 2026-09-08 | 2026-09-10 | 3 |  | Not Started | 0% | Y | Entity list with volumes; feeds migration sizing
1.4 | M1. Discovery & Inventory | List all auth methods, IdPs, token and session mechanisms | Security Lead | 2026-09-09 | 2026-09-10 | 2 |  | Not Started | 0% | Y | Needed before any identity decision
1.5 | M1. Discovery & Inventory | Catalog public APIs, webhooks, SDKs and their active consumers | API Owner | 2026-09-09 | 2026-09-11 | 3 |  | Not Started | 0% | Y | Include call volumes per endpoint to rank what must survive
1.6 | M1. Discovery & Inventory | Catalog third-party integrations, vendors, licences, renewal dates | Ops / Procurement | 2026-09-09 | 2026-09-11 | 3 |  | Not Started | 0% | N | Renewal dates drive the decommission notice periods
1.7 | M1. Discovery & Inventory | Map customer and tenant overlap (accounts present on both systems) | CS Lead | 2026-09-09 | 2026-09-11 | 3 | 1.3 | Not Started | 0% | Y | Overlap list drives dedup rules and pilot selection
1.8 | M1. Discovery & Inventory | Compile compliance obligations: SOC 2, ISO, GDPR, data residency | Compliance | 2026-09-10 | 2026-09-11 | 2 |  | Not Started | 0% | Y | Merged system is a new audit boundary
1.9 | M1. Discovery & Inventory | Write gap and overlap analysis; hold review session | PM / Eng Leads | 2026-09-11 | 2026-09-11 | 1 | 1.1 | Not Started | 0% | Y | GATE: discovery signed off before architecture decision
1b.1 | M1b. Defect Triage & Data Integrity | Pull the full defect backlog from the broken system and de-duplicate it | Eng Lead (broken sys) | 2026-09-09 | 2026-09-10 | 2 | 0.2 | Not Started | 0% | Y | Include unlogged known issues; ask support, not just the tracker
1b.2 | M1b. Defect Triage & Data Integrity | Confirm WHICH system is broken: the surviving one or the retiring one | Exec Sponsor / Architect | 2026-09-09 | 2026-09-09 | 1 | 1b.1 | Not Started | 0% | Y | GATE: if the SURVIVING system is the broken one, stop and re-plan - see Legend tab
1b.3 | M1b. Defect Triage & Data Integrity | Classify every defect: data-corrupting / behavioural / cosmetic | Eng Lead + Data Lead | 2026-09-10 | 2026-09-14 | 3 | 1b.1 | Not Started | 0% | Y | Only the data-corrupting class threatens the merge
1b.4 | M1b. Defect Triage & Data Integrity | Quantify the corruption blast radius: which entities, how many records | Data Lead | 2026-09-11 | 2026-09-16 | 4 | 1b.3 | Not Started | 0% | Y | Record counts per defect; this sizes the cleansing effort
1b.5 | M1b. Defect Triage & Data Integrity | Decide fix vs retire per defect and freeze everything else | Exec Sponsor / Eng Lead | 2026-09-15 | 2026-09-15 | 1 | 1b.4 | Not Started | 0% | Y | GATE: do NOT fix bugs in a system you are retiring unless they corrupt migrating data
1b.6 | M1b. Defect Triage & Data Integrity | Run data-quality profiling: nulls, orphans, duplicates, broken FKs, out-of-range values | Data Lead | 2026-09-11 | 2026-09-17 | 5 | 1.3 | Not Started | 0% | Y | Must finish BEFORE the ETL mapping spec is frozen (4.1)
1b.7 | M1b. Defect Triage & Data Integrity | Fix only the data-corrupting defects; everything else stays broken | Eng Team | 2026-09-16 | 2026-09-23 | 6 | 1b.5 | Not Started | 0% | Y | Stops the bleeding so migrated data does not keep degrading
1b.8 | M1b. Defect Triage & Data Integrity | Write cleansing and quarantine rules for records that cannot be repaired | Data Lead | 2026-09-17 | 2026-09-23 | 5 | 1b.6 | Not Started | 0% | Y | Three buckets: repair, quarantine, leave behind
1b.9 | M1b. Defect Triage & Data Integrity | Decide the policy for known-bad records: migrate, quarantine, or abandon | Exec Sponsor / Legal | 2026-09-21 | 2026-09-23 | 3 | 1b.8 | Not Started | 0% | Y | Customer-visible; may need contractual or regulatory input
1b.10 | M1b. Defect Triage & Data Integrity | Stabilisation gate: error rate flat for 3 consecutive days before dry runs | Eng Lead | 2026-09-23 | 2026-09-24 | 2 | 1b.7 | Not Started | 0% | Y | GATE: migrating off a still-degrading system invalidates every dry run
2.0 | M2. Target Architecture Decision | Re-weight the architecture options against the defect profile | Architect | 2026-09-14 | 2026-09-14 | 1 | 1b.3 | Not Started | 0% | Y | A badly broken system is a strong argument for absorb-and-retire over unify
2.1 | M2. Target Architecture Decision | Draft 2-3 architecture options with cost, risk and time estimates | Architect | 2026-09-10 | 2026-09-11 | 2 | 1.9 | Not Started | 0% | Y | Absorb A into B / unify behind shared shell / rebuild
2.2 | M2. Target Architecture Decision | Run decision workshop and choose the strategy | Exec Sponsor | 2026-09-14 | 2026-09-14 | 1 | 2.0 | Not Started | 0% | Y | GATE: one option chosen, in writing, same day
2.3 | M2. Target Architecture Decision | Write ADR including sunset date for the retiring system | Architect | 2026-09-14 | 2026-09-14 | 1 | 2.2 | Not Started | 0% | Y | Sunset date is a commitment, not an aspiration
2.4 | M2. Target Architecture Decision | Publish the 'will NOT unify by 1 Oct' scope list | PM | 2026-09-14 | 2026-09-14 | 1 | 2.2 | Not Started | 0% | Y | Primary defence against scope creep
2.5 | M2. Target Architecture Decision | Exec sponsor sign-off on architecture and scope | Exec Sponsor | 2026-09-14 | 2026-09-14 | 1 | 2.3 | Not Started | 0% | Y | GATE: build work does not start before this
3.1 | M3. Identity & Access Unification | Choose the canonical identity provider | Security Lead | 2026-09-15 | 2026-09-15 | 1 | 2.5 | Not Started | 0% | Y | Everything downstream depends on this
3.2 | M3. Identity & Access Unification | Define the unified user and org / tenant model | Architect | 2026-09-15 | 2026-09-16 | 2 | 3.1 | Not Started | 0% | Y | Tenant model must cover customers on both systems
3.3 | M3. Identity & Access Unification | Map roles and permissions A to B and resolve conflicts | Security Lead | 2026-09-16 | 2026-09-17 | 2 | 3.2 | Not Started | 0% | Y | Deliberately decide every case where A is more permissive than B
3.4 | M3. Identity & Access Unification | Define user dedup and merge rules (same email, different accounts) | Data Lead | 2026-09-16 | 2026-09-18 | 3 | 3.2 | Not Started | 0% | Y | Covers same person, two orgs, and conflicting profile data
3.5 | M3. Identity & Access Unification | Implement SSO / token bridge between the two systems | Eng Team | 2026-09-17 | 2026-09-23 | 5 | 3.3 | Not Started | 0% | Y | One login gets the user into both surfaces
3.6 | M3. Identity & Access Unification | Test login, session, permission enforcement and edge cases | QA | 2026-09-22 | 2026-09-24 | 3 | 3.5 | Not Started | 0% | Y | GATE: no privilege escalation across the merged boundary
3.7 | M3. Identity & Access Unification | Plan password / MFA re-enrolment comms for affected users | CS Lead | 2026-09-23 | 2026-09-24 | 2 | 3.5 | Not Started | 0% | N | Send before cutover, not after
4.1 | M4. Data Model Mapping & Migration | Define canonical entities and field-level mapping spec | Data Lead | 2026-09-17 | 2026-09-19 | 2 | 1b.6 | Not Started | 0% | Y | GATE: cannot be frozen until data-quality profiling (1b.6) is done
4.2 | M4. Data Model Mapping & Migration | Decide ID collision strategy (namespace / remap / new UUIDs) | Architect | 2026-09-15 | 2026-09-16 | 2 | 4.1 | Not Started | 0% | Y | Keep a permanent old-ID to new-ID lookup table
4.3 | M4. Data Model Mapping & Migration | Define dedup and conflict-resolution rules per entity | Data Lead | 2026-09-19 | 2026-09-21 | 1 | 1b.8 | Not Started | 0% | Y | A corrupted record must never win a conflict against a clean one
4.4 | M4. Data Model Mapping & Migration | Build migration ETL scripts including cleansing transforms | Eng Team | 2026-09-19 | 2026-09-24 | 4 | 4.1 | Not Started | 0% | Y | Must be idempotent and re-runnable
4.5 | M4. Data Model Mapping & Migration | Build reconciliation suite: row counts, checksums, spot audits | Data Lead | 2026-09-18 | 2026-09-24 | 5 | 4.4 | Not Started | 0% | Y | Must separate PRE-EXISTING corruption from loss caused by the migration
4.6 | M4. Data Model Mapping & Migration | Dry run 1 against a production copy; log every failure | Eng Team | 2026-09-24 | 2026-09-25 | 2 | 4.5 | Not Started | 0% | Y | Expect it to fail; that is the point
4.7 | M4. Data Model Mapping & Migration | Fix defects and run dry run 2 until reconciliation passes clean | Eng Team | 2026-09-25 | 2026-09-28 | 2 | 4.6 | Not Started | 0% | Y | GATE: zero unexplained record deltas
4.8 | M4. Data Model Mapping & Migration | Timed rehearsal (dry run 3) to measure the real cutover window | Eng Team | 2026-09-28 | 2026-09-29 | 2 | 4.7 | Not Started | 0% | Y | Gives the maintenance window you announce to customers
4.9 | M4. Data Model Mapping & Migration | Write and actually test the rollback procedure | Eng Lead | 2026-09-28 | 2026-09-29 | 2 | 4.7 | Not Started | 0% | Y | Untested rollback is not a rollback
4.10 | M4. Data Model Mapping & Migration | Schedule full-fleet migration waves (executed after 1 Oct) | PM | 2026-09-29 | 2026-09-30 | 2 | 4.8 | Not Started | 0% | N | Out of scope for 1 Oct; scheduled, not executed
5.1 | M5. Billing & Subscription Consolidation | Map all plans and SKUs A to B; flag orphan plans | Finance / Product | 2026-09-15 | 2026-09-17 | 3 | 2.5 | Not Started | 0% | Y | Long pole: this is legal and finance work, not just code
5.2 | M5. Billing & Subscription Consolidation | Decide grandfathering and proration policy | Finance | 2026-09-17 | 2026-09-18 | 2 | 5.1 | Not Started | 0% | Y | Decide before any customer is told anything
5.3 | M5. Billing & Subscription Consolidation | Legal review: contract amendments and notice periods required | Legal | 2026-09-17 | 2026-09-23 | 5 | 5.1 | Not Started | 0% | Y | Notice periods may hard-block your cutover date
5.4 | M5. Billing & Subscription Consolidation | Choose the single billing system of record | Finance | 2026-09-18 | 2026-09-18 | 1 | 5.1 | Not Started | 0% | Y | One system issues invoices from cutover onward
5.5 | M5. Billing & Subscription Consolidation | Build subscription migration and proration logic | Eng Team | 2026-09-21 | 2026-09-29 | 7 | 5.4 | Not Started | 0% | Y | Reuses the ID mapping from 4.2
5.6 | M5. Billing & Subscription Consolidation | Finance sign-off: revenue recognition, invoicing, tax treatment | Finance | 2026-09-28 | 2026-09-30 | 3 | 5.5 | Not Started | 0% | Y | GATE: no cutover without this
5.7 | M5. Billing & Subscription Consolidation | Generate test invoices for the pilot cohort (dry run, no charges) | Finance / Eng | 2026-09-29 | 2026-09-30 | 2 | 5.5 | Not Started | 0% | Y | Compare against what each account paid last cycle
6.1 | M6. API & Integration Compatibility | Decide the surviving API surface and versioning scheme | API Owner | 2026-09-16 | 2026-09-17 | 2 | 2.5 | Not Started | 0% | Y | Ranked by consumer call volume from 1.5
6.2 | M6. API & Integration Compatibility | Publish the deprecation policy with concrete dates | API Owner | 2026-09-17 | 2026-09-18 | 2 | 6.1 | Not Started | 0% | Y | Customers need dates, not intentions
6.3 | M6. API & Integration Compatibility | Build the compatibility shim for retired endpoints | Eng Team | 2026-09-18 | 2026-09-25 | 6 | 6.1 | Not Started | 0% | Y | Buys time; avoids breaking integrations at cutover
6.4 | M6. API & Integration Compatibility | Rebuild webhooks and event contracts | Eng Team | 2026-09-21 | 2026-09-25 | 5 | 6.1 | Not Started | 0% | Y | Payload shape changes break silently; version them
6.5 | M6. API & Integration Compatibility | Re-point third-party integrations and get partner confirmations | Partnerships | 2026-09-22 | 2026-09-29 | 6 | 6.3 | Not Started | 0% | Y | Partners have their own release cycles; start early
6.6 | M6. API & Integration Compatibility | Send migration guide to all API consumers | API Owner | 2026-09-23 | 2026-09-25 | 3 | 6.2 | Not Started | 0% | N | Include a working code example, not just a changelog
7.1 | M7. Unified Experience | Agree unified terminology and glossary (objects, plan names) | Product | 2026-09-17 | 2026-09-18 | 2 | 2.5 | Not Started | 0% | N | Two names for one concept is the most visible merge smell
7.2 | M7. Unified Experience | Deliver one login and a single entry point | Eng Team | 2026-09-21 | 2026-09-25 | 5 | 3.5 | Not Started | 0% | Y | Minimum bar: customer does not feel they use two products
7.3 | M7. Unified Experience | Merge navigation and app shell | Eng Team | 2026-09-22 | 2026-09-29 | 6 | 7.2 | Not Started | 0% | N | Full design-system convergence is post-1 Oct
7.4 | M7. Unified Experience | Reconcile critical shared flows: onboarding, settings, billing UI | Product / Eng | 2026-09-23 | 2026-09-29 | 5 | 7.2 | Not Started | 0% | Y | Only the flows a pilot customer will hit this month
7.5 | M7. Unified Experience | Update help docs, in-app guides, emails and status page | Content / CS | 2026-09-24 | 2026-09-30 | 5 | 7.1 | Not Started | 0% | N | Stale docs generate the first wave of tickets
7.6 | M7. Unified Experience | Accessibility and cross-browser pass on the merged shell | QA | 2026-09-28 | 2026-09-30 | 3 | 7.3 | Not Started | 0% | N | Can slip past 1 Oct if the pilot cohort is small
8.1 | M8. Infrastructure & Operations Merge | Decide hosting target and network / VPC topology | Infra Lead | 2026-09-15 | 2026-09-16 | 2 | 2.5 | Not Started | 0% | Y | Data residency from 1.8 constrains this
8.2 | M8. Infrastructure & Operations Merge | Merge CI/CD pipelines and secrets management | Infra Lead | 2026-09-16 | 2026-09-23 | 6 | 8.1 | Not Started | 0% | Y | One deploy path before you migrate any customer
8.3 | M8. Infrastructure & Operations Merge | Unify observability: logs, metrics, traces, alerting | Infra Lead | 2026-09-18 | 2026-09-25 | 6 | 8.2 | Not Started | 0% | Y | You cannot run hypercare blind
8.4 | M8. Infrastructure & Operations Merge | Establish a single on-call rota and incident runbook | Infra Lead | 2026-09-22 | 2026-09-25 | 4 | 8.3 | Not Started | 0% | Y | One rota, one pager, one severity scale
8.5 | M8. Infrastructure & Operations Merge | Security review of the new trust boundary; scope a pen test | Security Lead | 2026-09-23 | 2026-09-29 | 5 | 8.1 | Not Started | 0% | Y | Full pen test almost certainly lands after 1 Oct
8.6 | M8. Infrastructure & Operations Merge | Update compliance scope: audit boundary, DPAs, subprocessor list | Compliance | 2026-09-23 | 2026-09-30 | 6 | 1.8 | Not Started | 0% | Y | Customers with DPAs may require advance notice
8.7 | M8. Infrastructure & Operations Merge | Capacity and load test the merged system | Infra Lead | 2026-09-28 | 2026-09-30 | 3 | 8.3 | Not Started | 0% | Y | Merged load is not the sum of two idle systems
9.1 | M9. Phased Customer Migration (Pilot) | Select the pilot cohort - exclude accounts with known corrupted data | CS Lead | 2026-09-24 | 2026-09-25 | 2 | 1b.4 | Not Started | 0% | Y | Small, engaged, clean data, no enterprise contract clauses
9.2 | M9. Phased Customer Migration (Pilot) | Enable support and CS: runbooks, FAQ, escalation path | CS Lead | 2026-09-25 | 2026-09-29 | 3 | 9.1 | Not Started | 0% | Y | GATE: enablement lands BEFORE the first wave, not after
9.3 | M9. Phased Customer Migration (Pilot) | Send customer comms: advance notice, timing, what changes | Marketing / CS | 2026-09-25 | 2026-09-29 | 3 | 9.1 | Not Started | 0% | Y | Respect any contractual notice period from 5.3
9.4 | M9. Phased Customer Migration (Pilot) | Execute the pilot cutover | Eng Team | 2026-09-30 | 2026-09-30 | 1 | 4.8 | Not Started | 0% | Y | GATE: go / no-go call the morning of, rollback armed
9.5 | M9. Phased Customer Migration (Pilot) | Hypercare monitoring: error rates, tickets, login success rate | Eng / CS | 2026-09-30 | 2026-10-01 | 2 | 9.4 | Not Started | 0% | Y | Pre-agreed thresholds that trigger rollback
9.6 | M9. Phased Customer Migration (Pilot) | Go / no-go review for wave 2; confirm remaining wave schedule | Exec Sponsor | 2026-10-01 | 2026-10-01 | 1 | 9.5 | Not Started | 0% | Y | GATE: 1 Oct deliverable is this decision, not a full merge
10.1 | M10. Decommission (planning only by 1 Oct) | Write legacy shutdown plan with data retention and archival policy | Architect | 2026-09-29 | 2026-09-30 | 2 | 2.3 | Not Started | 0% | N | Retention obligations from 1.8 apply
10.2 | M10. Decommission (planning only by 1 Oct) | List vendor and licence terminations with their notice dates | Procurement | 2026-09-29 | 2026-09-30 | 2 | 1.6 | Not Started | 0% | N | Miss a notice date and you auto-renew for a year
10.3 | M10. Decommission (planning only by 1 Oct) | Baseline the expected cost saving and name an owner to track it | Finance | 2026-09-30 | 2026-10-01 | 2 | 10.2 | Not Started | 0% | N | Savings are not real until the old stack is off
10.4 | M10. Decommission (planning only by 1 Oct) | Roadmap the out-of-scope items deferred past 1 Oct | PM | 2026-10-01 | 2026-10-01 | 1 | 2.4 | Not Started | 0% | Y | Closes the loop on the scope list from 2.4
Formulas:
Work Days = NETWORKDAYS([Start],[End])

## Milestone Summary
Milestone Rollup & Programme Status
Every figure below is a formula reading the 'Merge Plan' tab. Update the plan, not this sheet.
Deadline | 2026-10-01
Working days remaining (from today's date) | 18
Total tasks | 83
Tasks complete | 0
Tasks blocked | 0
Overall % complete | 0%
Critical-path tasks still open | 71
Milestone | Tasks | Done | Blocked | Start | Finish | % Complete | Status
M0. Program Setup | 5 | 0 | 0 | 2026-09-08 | 2026-09-09 | 0% | Not Started
M1. Discovery & Inventory | 9 | 0 | 0 | 2026-09-08 | 2026-09-11 | 0% | Not Started
M1b. Defect Triage & Data Integrity | 10 | 0 | 0 | 2026-09-09 | 2026-09-24 | 0% | Not Started
M2. Target Architecture Decision | 6 | 0 | 0 | 2026-09-10 | 2026-09-14 | 0% | Not Started
M3. Identity & Access Unification | 7 | 0 | 0 | 2026-09-15 | 2026-09-24 | 0% | Not Started
M4. Data Model Mapping & Migration | 10 | 0 | 0 | 2026-09-15 | 2026-09-30 | 0% | Not Started
M5. Billing & Subscription Consolidation | 7 | 0 | 0 | 2026-09-15 | 2026-09-30 | 0% | Not Started
M6. API & Integration Compatibility | 6 | 0 | 0 | 2026-09-16 | 2026-09-29 | 0% | Not Started
M7. Unified Experience | 6 | 0 | 0 | 2026-09-17 | 2026-09-30 | 0% | Not Started
M8. Infrastructure & Operations Merge | 7 | 0 | 0 | 2026-09-15 | 2026-09-30 | 0% | Not Started
M9. Phased Customer Migration (Pilot) | 6 | 0 | 0 | 2026-09-24 | 2026-10-01 | 0% | Not Started
M10. Decommission (planning only by 1 Oct) | 4 | 0 | 0 | 2026-09-29 | 2026-10-01 | 0% | Not Started
TOTAL | 83 | 0 | 0 | 2026-09-08 | 2026-10-01 | 0%
Formulas:
Start = MINIFS('Merge Plan'!$E5:E87,'Merge Plan'!$B5:B87,[Milestone])
Start = MIN(E13:[Start, row above])
Finish = MAXIFS('Merge Plan'!$F5:F87,'Merge Plan'!$B5:B87,[Milestone])
Finish = MAX(F13:[Finish, row above])

## Legend & Assumptions
How to use this workbook
EDIT THESE COLUMNS on the 'Merge Plan' tab | Owner, Start, End, Status, % Done - shown as blue text on a yellow fill.
DO NOT EDIT | Work Days is a NETWORKDAYS formula. The whole 'Milestone Summary' tab is formulas.
Status values | Not Started / In Progress / Blocked / Done / Deferred (dropdown on the Status column).
Critical Path = Y | Slipping this task slips the 1 Oct date. There are no spare days to absorb it.
GATE in the Notes column | A hard stop. Do not begin dependent work until that exit criterion is met.
EXAMPLE ROW - this is the format expected in the editable columns
ID | Milestone | Task | Owner | Start | End | Status | % Done
1.4 | M1. Discovery & Inventory | List all auth methods, IdPs, token and session mechanisms | A. Ben Salah | 2026-09-09 | 2026-09-10 | In Progress | 60%
Assumptions behind the dates
- Start 8 Sep 2026 and deadline 1 Oct 2026 were both supplied by the user.
- 18 working days are available in that window (weekends excluded, no public holidays assumed - adjust if Tunisian holidays apply).
- This window is NOT enough to complete a full SaaS merge. Data migration and billing consolidation normally run for months.
- The plan is therefore scoped to: discovery, architecture decision, identity unification, a tested and reconciled migration, and a PILOT cutover on 30 Sep.
- The 1 Oct deliverable is milestone M9.6 - a go/no-go decision plus a signed wave schedule - not a fully migrated customer base.
- Explicitly deferred past 1 Oct: full-fleet migration (4.10), complete design-system convergence (7.3), penetration testing (8.5), and legacy decommission (M10).
- Owner names are role placeholders. Replace them with real people; one unnamed owner is the most common cause of slippage.
- Task durations assume a dedicated team from both systems, not people fitting this around a normal roadmap.
- Every milestone can be compressed except M4 (migration dry runs), M5.3 (legal notice periods) and M1b (defect stabilisation), which are bounded by reality rather than effort.
- One of the two systems is reported as buggy (user-supplied). Milestone M1b was added for defect triage and data-integrity work, and the ETL mapping spec (4.1) now waits on data-quality profiling (1b.6).
- M1b adds roughly a week of serial work in front of the migration. The pilot cutover on 30 Sep now has effectively zero float - see the Broken system guidance below.
Broken system - decision guidance (M1b)
QUESTION 1 - which system is broken?
If it is the RETIRING system: proceed with this plan. Fix almost nothing. Every hour spent on bugs in software you are deleting is an hour stolen from the migration.
If it is the SURVIVING system: stop and re-plan. Merging onto an unstable base means every migrated customer lands on broken software, and during hypercare you cannot tell merge defects from pre-existing ones. Stabilise first, then merge.
QUESTION 2 - are the bugs behavioural or data-corrupting?
Behavioural (crashes, wrong output, broken UI): these die with the retired system. Log them, do not fix them.
Data-corrupting (orphans, broken foreign keys, duplicate entities, wrong values persisted): these MIGRATE. Once in the merged system they are permanent and expensive to unwind. Fix the source, then cleanse, then migrate.
QUESTION 3 - is the corruption still spreading?
If the defect is still writing bad data, every dry run is invalidated the moment it finishes. Task 1b.10 is the gate: error rate flat for three consecutive days before dry run 1.
The rule to hold onto: do not migrate data you cannot vouch for. Quarantining a bad record is recoverable. Silently importing it into the surviving system is not.